COMPUTER PROJECT – PROCESS STEPS & NEEDS

| STEPS | # PROCESS STEP | # NGO Responsible | # To Date Information | # Outstanding Information |
| --- | --- | --- | --- | --- |
|  | # Define objective for the deployment of computers | # SEWA | # enhance communication between its members and various centers # create a database of the information related to healthcare, trade, etc. # computer education for younger generation # graphics design capability for women designers # accounting and financial management for micro-enterprises | # Hours of operation |
|  | # Define role of fellows | # SEWA/Asha | - Work with the IIM Computer Club - Work with software companies to develop software customized to SEWA needs - Participate in orientation of rural Gujarat – arranged by SEWA - Assess the current use of internet and identify strengths and weaknesses for moving forward - Install hardware and software across all districts - Train 300 – 400 people in 25 SEWA centers - Monitor the progress in government schools - Monitor and measure the progress at SEWA sites - Facilitate lateral learning between centers (covering 900 villages) # Strengthen SEWA IT center |  |
|  | # Establish measurement metrics | # Asha/SEWA |  |  |
|  | # Identify software needed to support the objectives and develop curriculum. | # Asha/SEWA |  |  |
|  | # Translate curriculum and training material into local languages | # Asha/SEWA |  |  |
|  | # Identify sites to receive computers - Number of sites - Number of computers at each site - Relative location of the sites with respect to each other | # SEWA | ## 25 SEWA & 8 – 10 Govt sites | # # of computers at each site - See Appendix A for a list of 15 SEWA sites. Required 10 more SEWA site locations and government locations |
|  | # Deal with government schools | # SEWA |  | # Government thinking of bringing 10,000 computers. How does this fit with our plan? - Should the government sites be in villages or Ahmedabad? - What is the skill set of existing teachers? |
|  | # Recruit teachers and procure funds to support teachers | # SEWA |  | # Will the government schools hire new teachers or train existing teachers? - If new teachers are needed, who is responsible for recruitment? |
|  | # Enroll students | # SEWA |  |  |
|  | Procure computers and monitors from corporations. Verify the items for the following: - Computer and Monitor enabled for 220V & 50Hz - Power cables - Operating System - Mouse and Mouse Pad - Keyboard - Network card - Modem - Cable to connect computer and monitor | # WCE |  | # Spare parts shipment? - A certain % of the computers may not be working when received in India. How do we plan for that ? |
|  | Storage and transportation of computers within USA | # WCE |  |  |
|  | - Transportation of computers to India | # WCE |  |  |
|  | - Decide on port of entry | # SEWA/WCE |  |  |
|  | - Arrange custom clearance papers | # SEWA |  |  |
|  | - Arrange for custom clearance at the port of entry | - SEWA |  |  |
|  | - Unloading of computer systems for shipment within India | # SEWA |  |  |
|  | - Arrange funds, insurance and shipper for shipping within India | - SEWA |  |  |
|  | Site Survey and preparation - Adequate space for at least 10 computers - Furniture and related "office" equipment - Dedicated analog phone lines for Internet dialup connectivity - Two external modems (one for backup) - One UPS of at least 1200va for the server (one machine will be a server as we are in fact installing a small network in each school) - A 16 port Hub - Surge suppressors and stabilizers for each computer and hub (11) - AC outlets and electrical capacity - At least one printer - Scanner (optional) - Air-conditioning if required - Wiring and installation - Security arrangements - Medium run sustainability | SEWA |  | - Printer type needs definition? - Library space? |
|  | - Teacher training and documentation of procedures for computer usage. Post installation software and training support | - Asha |  |  |
|  | ## Maintenance and support for equipment (including supplies) | - SEWA |  | - Funds to pay for telephone connection charges and maintenance? |
|  | ## Recruit 6 Asha fellows | - SEWA/Asha |  | - Logistical support for fellows |
|  | ## Fundraising for 6 Asha Fellows @ $2,400 a fellow | - Asha | - Secured funds for 3 fellows | - Need funds for 3 more fellows ($7,200) |
|  | ## Fundraising for UPSs and printers | - SEWA |  | - Need $41,335 |
|  | After school hours use of computers for revenue generating activities | Asha/ SEWA |  |  |
|  | Connection of schools in India to US schools | SEWA/WCE |  |  |
|  | Exchange of students from US schools to India | SEWA/WCE |  |  |
|  | Partnership with technical and management schools | Vichaar |  |  |

APPENDIX A

List of Computer Sites

|  | SITE NAME | SITE LOCATION |
| --- | --- | --- |
|  | Banaskantha DWCRA Mahila SEWA Association | Suleman Bhagat Bunglow, Opp. Marketyard, Radhanpur, Dist. Banaskantha, Tel/Fax: 02746-77218 |
|  | Banaskantha DWCRA Mahila SEWA Association | C/o Jomiben Jayrambhai Rajgor, Village Madhutra, Santalpur., Patan |
|  | Kutch Craft Association. | 25, Bankers Colony, Akashvani Bhavan, C/o Kamalkant Bhatt House, Kutch-Bhuj, Tel/Fax: 02832-21971 |
|  | Kutch Craft Association | Court’s Compound of the Taluka Panchayat, Naliya, Kutch |
|  | Kutch Craft Association | Opp. Post Office, Nakhatrana, Kutch |
|  | Kutch Craft Association | Opp. State Bank of India, Dayapar |
|  | Sabarkantha Khedu Mandal | Kotiyart Society, Opp. Sapan Hospital, C/o. premilaben Brambhatt House., Tel/Fax: 02779-20327 |
|  | Kheda Savings & Credit Association | Gangotri Complex, Near Central Bank Road., Mefer Road, Anand. Tel/Fax: 02612-54844 |
|  | Sukhi Mahila SEWA Mandal | Kubernagar Society, Near Taslim Garage, C/o Biharibhai's House, Daboi Road, Bodeli Dist.Baroda, Tel/Fax: 02665-20713 |
|  | Self Employed Women's Association | SEWA Reception Centre, Opp. Lok Manya Tilak Baug, Bhadra, Ahmedabad |
|  | SEWA Academy | Nr.Hariharanand Ashram, Nr. Ellisbridge Corner, Ahmedabad – 380 006 |
|  | Surendranagar Mahila and Balvikash Mandal | Valabai's Place, Jogasar Road, Dhangadhra Road, Surendranagr, Tel/Fax : 02754/50829 |
|  | # Ganeshpura Tree Growers Mandal | Taluka : Kadi, Ganeshpura, Nandasan Road., District : Mehsana |
|  | Ahmedabad Management Association | CORE – AMA Management House, Torent – AMA Management Centre Atira Campus, Dr. Vikram Sarabhai Marg, Ahmedabad – 380 015 |